## Summary
Group Assignment Summary
Team Member | Primary Contribution | Related Task ID(s) | Status
Nicholas Roberts | Individual SQL HW6 submission; created Gantt chart | 2, 8 | Complete
Frankie Liang | Individual SQL HW6 submission; completed Excel to-do sheet | 3, 5 | Complete
Simran Singh | Individual SQL HW6 submission; created walkthrough video | 4, 7 | Complete

## Gantt Chart
SQL HW6 Group Assignment - Gantt Chart
Team: Nicholas Roberts, Frankie Liang, Simran Singh
Legend | Nicholas | Frankie | Simran | Team |  | Complete | In Progress | Not Started
Task ID | Task | Owner | Start Date | End Date | Duration (days) | Status | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16
1 | Review assignment requirements and Chapter 6 set operators | Team | 2026-03-09 | 2026-03-10 | 2 | Complete | bar: 2026-03-09 to 2026-03-10
2 | Nicholas completes individual SQL HW6 submission | Nicholas Roberts | 2026-03-10 | 2026-03-12 | 3 | Complete | bar: 2026-03-10 to 2026-03-12
3 | Frankie completes individual SQL HW6 submission | Frankie Liang | 2026-03-10 | 2026-03-12 | 3 | Complete | bar: 2026-03-10 to 2026-03-12
4 | Simran completes individual SQL HW6 submission | Simran Singh | 2026-03-10 | 2026-03-12 | 3 | Complete | bar: 2026-03-10 to 2026-03-12
5 | Frankie prepares Excel to-do sheet | Frankie Liang | 2026-03-11 | 2026-03-12 | 2 | Complete | bar: 2026-03-11 to 2026-03-12
6 | Group check-in and combine individual work | Team | 2026-03-13 | 2026-03-13 | 1 | Complete | bar: 2026-03-13
7 | Simran records and edits project walkthrough video | Simran Singh | 2026-03-14 | 2026-03-15 | 2 | Complete | bar: 2026-03-14 to 2026-03-15
8 | Nicholas creates Gantt chart | Nicholas Roberts | 2026-03-15 | 2026-03-15 | 1 | Complete | bar: 2026-03-15
9 | Final review and submit MP4 + SQL files | Team | 2026-03-16 | 2026-03-16 | 1 | Complete | bar: 2026-03-16
Notes
Timeline shown is a simple project schedule for the group assignment and can be edited if your instructor gave different dates.

## Chart Data
Task | Start Offset | Duration
Review assignment requirements and Chapter 6 set operators | 0 | 2
Nicholas completes individual SQL HW6 submission | 1 | 3
Frankie completes individual SQL HW6 submission | 1 | 3
Simran completes individual SQL HW6 submission | 1 | 3
Frankie prepares Excel to-do sheet | 2 | 2
Group check-in and combine individual work | 4 | 1
Simran records and edits project walkthrough video | 5 | 2
Nicholas creates Gantt chart | 6 | 1
Final review and submit MP4 + SQL files | 7 | 1

## Gantt Bar Chart
Use the Gantt Chart sheet for the editable timeline grid.